## Summary
Aspire Test suites
Version | Write by | Revision Date | Approved By | Approval Date | Outline
#
# | Phuoc Ha (Erit) | 2020-09-21 |  |  | Init draft
# | Phuoc Ha (Erit)
Test Result Summary
| Total Testcases | Pass | Fail | NOT RUN | Not Tested
| 37 | 27 | 0 | 1 | 9
| % | 72.97% | 0% | 2.703% | 24.32%
DBS IBG SG Test suites
URL Domain (STG) | https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/
Team Members
Members
Erit Ha
Member 01
Member 02
Member 03
Member 04
Member 05
Member 06
Member 07
Member 08

## Test Outline
Test Coverage
Module | Test Case ID | Test name | Main check | Execution result | Actual Result | Automation status | Note
Register Suite | REG_001 | Verify registered director account successfully and Incorporated | + New user registered successfully + All elements of each page should be displayed correctly + User should go to Onboarding page and add more infomations | PASSED |  | Yes
| REG_002 | Verify new account unincorporated country when opening new account as director | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | PASSED |  | Yes
| REG_003 | Verify new account unincorporated country when opening new account as non employee | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | PASSED |  | Yes
| REG_004 | Verify new account unincorporated country when opening new account as freelancer | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | PASSED |  | Yes
| REG_005 | Verify new account created to Incorporate my company | + New user registered successfully + All elements of each page should be displayed correctly + User should go to Aspire Incorporated page after selecting the business "Open New Account To Incorporate My Company();" | PASSED |  | Yes
| REG_006 | Verify new account register is existed and associated | Message should be shown: "The email has already been taken." and "The phone has already been taken." | PASSED |  | Yes
| REG_007 | Verity empty fullname | Message should be shown: "Full Name as per ID is required." | PASSED |  | Yes
| REG_008 | Verity empty email | Message should be shown: "Email address is required." | PASSED |  | Yes
| REG_009 | Verify empty phone number | Message should be shown: "Mobile number is required." | PASSED |  | Yes
| REG_010 | Verify the email contains special character | Message should be shown: "Email address must be a valid email address." | PASSED |  | Yes
| REG_011 | Verify the email missing name | Message should be shown: "Email address must be a valid email address." | PASSED |  | Yes
| REG_012 | Verify the email missing @ domain | Message should be shown: "Email address must be a valid email address." | PASSED |  | Yes
| REG_013 | Verify invalid email domain | Message should be shown: "Email address must be a valid email address." | PASSED |  | Yes
| REG_014 | Verify the invalid phone number with length more than 14 characters | Message should be shown: "Verify the invalid phone number with length more than 14 characters" | PASSED |  | Yes
| REG_015 | Verify the invalid phone number contains string | Message should be shown: "Incorrect phone format for phone., The phone format is invalid." | PASSED |  | Yes
| REG_016 | Verify valid referral code |  | NOT RUN |  | NOT YET
| REG_017 | Verify Invalid referral code |  | NOT RUN |  | NOT YET
| REG_018 | Verify registered employee account successfully and Incorporated |  | NOT RUN |  | NOT YET
| REG_019 | Verify registered employee account successfully and Incorporated |  | NOT RUN |  | NOT YET
| REG_020 | Verify registered freelancer account successfully and Incorporated |  | NOT RUN |  | NOT YET
| REG_021 | Verify registered entrepreneur account successfully and Incorporated |  | NOT RUN |  | NOT YET
| REG_022 | Verify onboarding personal detail form |  | NOT RUN |  | NOT YET
| REG_023 | Verify onboarding business detail form |  | NOT RUN |  | NOT YET
| REG_024 | Verify onboarding identify detail form |  | NOT RUN |  | NOT YET
Login Suite | LOG_001 | Verify the Login page should be displayed correctly | Login page should be display correctly | PASSED |  | Yes
| LOG_002 | Verify the existing user email login successfully | Home page should be display correctly | PASSED |  | Yes
| LOG_003 | Verify the existing phone number login successfully | Home page should be display correctly | PASSED |  | Yes
| LOG_004 | Verity unregistered email | Message should be shown: "The entered email address is invalid." | PASSED |  | Yes
| LOG_005 | Verity unregistered phone number | Message should be shown: "The entered phone number is invalid." | PASSED |  | Yes
| LOG_006 | Verify empty username | Message should be shown: "The phone field is required when email is not present." | PASSED |  | Yes
| LOG_007 | Verify the email contains special character | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_008 | Verify the email missing name | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_009 | Verify the email missing @ domain | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_010 | Verify invalid email domain | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_011 | Verify the invalid phone number with length more than 21 characters | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_012 | Verify the invalid phone number contains string | Message should be shown: "Registered email or phone is invalid" | PASSED |  | Yes
| LOG_013 | Some other negative tests |  | SKIP |  | No

## Register Suite
NOT RUN | 10 | [9 empty] | 10
FAILED | 0 | [9 empty] | 0
NOT RUN | 0 | [9 empty] | 0
NOT TEST | 3 | [9 empty] | 3
TOTAL TCs | 13 | [9 empty] | 13
Module | TCID | Precondition | Test name | Test steps detail | Expected | Main check | Actual Result | Priority | Tested By | Tested Date | Execution Result on UAT 21/09/2021 | Automated | Note
Positive | REG_001 | N/I | Verify registered director account successfully and Incorporated | 1. Go to aspire login page https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid info & submit (Singapore) 5. Verify user created successful 6. Click continue button to go business page 7. Select new account as director and click continue 8. Select more personal information details (Singapore) 9. Verify the Onboarding page shown successfully 10. Click button "Get Started" for Standard registration 11. Verify the Personal detail and input more info, then click continue 12. Verify the Business info and input valid date, then click continue 13. => I will ignore next steps for the onboarding with the KYC of Singapore | + New user registered successfully + All elements of each page should be displayed correctly + User should go to Onboarding page and add more infomations | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_002 | N/I | Verify new account unincorporated country when opening new account as director | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid info & submit (VietNam) 5. Verify user created successful 6. Click continue button to go business page 7. Select new account as director and click continue 8. Select more additional information details like company registered (Angola) 9. Verify the business unincorporated in Angola | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_003 | N/I | Verify new account unincorporated country when opening new account as non employee | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid info & submit (VietNam) 5. Verify user created successful 6. Click continue button to go business page 7. Select new account as non employee and click continue 8. Select more additional information details like company registered (Angola) 9. Verify the business unincorporated in Angola | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_004 | N/I | Verify new account unincorporated country when opening new account as freelancer | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid info & submit (VietNam) 5. Verify user created successful 6. Click continue button to go business page 7. Select new account as freelancer and click continue 8. Select more additional information details like company registered (Angola) 9. Verify the business unincorporated in Angola | + New user registered successfully + All elements of each page should be displayed correctly + User should go to unincorporated page after selecting the business | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_005 | N/I | Verify new account created to Incorporate my company | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid info & submit (VietNam) 5. Verify user created successful 6. Click continue button to go business page 7. Select new account to incorporate my company and click continue 8. Verify the Aspire Incorporated page should be displayed | + New user registered successfully + All elements of each page should be displayed correctly + User should go to Aspire Incorporated page after selecting the business "Open New Account To Incorporate My Company();" | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_006 | N/I | Verify new account register is existed and associated | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Input valid phone number "+65937892009" and email "erit09@gmail.com" 5. Dialog confirm the account associated should be display 6. Close the dialog | Message should be shown: "The email has already been taken." and "The phone has already been taken." | New user and all elements and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
Negative | REG_007 |  | Verity empty fullname | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Empty full name 5. Unforcused field | Message should be shown: "Full Name as per ID is required." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_008 |  | Verity empty email | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Empty email input 5. Unforcused field | Message should be shown: "Email address is required." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_009 |  | Verify empty phone number | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Empty phone number input 5. Unforcused field | Message should be shown: "Mobile number is required." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_010 |  | Verify the email contains special character | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid email "#@%^%#$@#$@#.com" 5. Unforcused field | Message should be shown: "Email address must be a valid email address." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_011 |  | Verify the email missing name | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid email "@gmail.com" 5. Unforcused field | Message should be shown: "Email address must be a valid email address." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_012 |  | Verify the email missing @ domain | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid email "invalidemail.gmail.com" 5. Unforcused field | Message should be shown: "Email address must be a valid email address." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_013 |  | Verify invalid email domain | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid email "invalidemail.gmail.com" 5. Unforcused field | Message should be shown: "Email address must be a valid email address." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_014 |  | Verify the invalid phone number with length more than 14 characters | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid phone number "9785422155569" 5. Unforcused field | Message should be shown: "Verify the invalid phone number with length more than 14 characters" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| REG_015 |  | Verify the invalid phone number contains string | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Click register link 3. Verify UI of Register page 4. Enter invalid phone number "93789ghtrt" 5. Click submit continue | Message should be shown: "Incorrect phone format for phone., The phone format is invalid." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
Others case not yet implemented | REG_016 |  | Verify valid referral code | [7 empty] | NOT RUN | NOT YET
| REG_017 |  | Verify Invalid referral code | [7 empty] | NOT RUN | NOT YET
| REG_018 |  | Verify registered employee account successfully and Incorporated | [7 empty] | NOT RUN | NOT YET
| REG_019 |  | Verify registered employee account successfully and Incorporated | [7 empty] | NOT RUN | NOT YET
| REG_020 |  | Verify registered freelancer account successfully and Incorporated | [7 empty] | NOT RUN | NOT YET
| REG_021 |  | Verify registered entrepreneur account successfully and Incorporated | [7 empty] | NOT RUN | NOT YET
| REG_022 |  | Verify onboarding personal detail form | [7 empty] | NOT RUN | NOT YET
| REG_023 |  | Verify onboarding business detail form | [7 empty] | NOT RUN | NOT YET
| REG_024 |  | Verify onboarding identify detail form | [7 empty] | NOT RUN | NOT YET

## Login Suite
NOT RUN | 10 | [9 empty] | 10
FAILED | 0 | [9 empty] | 0
NOT RUN | 1 | [9 empty] | 1
NOT TEST | 0 | [9 empty] | 0
TOTAL TCs | 11 | [9 empty] | 11
Module | TCID | Precondition | Test name | Test steps detail | Expected | Main check | Actual Result | Priority | Tested By | Tested Date | Execution Result on UAT 21/09/2021 | Automated | Note
Positive | LOG_001 | N/I | Verify the Login page should be displayed correctly | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ | Login page should be display correctly | All element and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_002 | + Account should be existed | Verify the existing user email login successfully | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email 3. Click "Next" button 4. Verify the home page should be displayed | Home page should be display correctly | All element and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_003 | + Account should be existed | Verify the existing phone number login successfully | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username phone number 3. Click "Next" button 4. Verify the home page should be displayed | Home page should be display correctly | All element and lable text posible |  | High | Erit Ha | 20/09/2021 | PASSED | Yes
Negative | LOG_004 | + Email not register | Verity unregistered email | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email (unregistered) "emailunregistered@gmail.com" 3. Click "Next" button 4. Verify the error message displayed | Message should be shown: "The entered email address is invalid." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_005 | + Phone not register | Verity unregistered phone number | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username phone number (unregistered) "09378923999" 3. Click "Next" button 4. Dialog confirm country should be display 5. User select country and submit next | Message should be shown: "The entered phone number is invalid." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_006 |  | Verify empty username | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Empty Valid 3. Click "Next" button | Message should be shown: "The phone field is required when email is not present." | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_007 |  | Verify the email contains special character | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email (unregistered) "#@%^%#$@#$@#.com" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_008 |  | Verify the email missing name | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email (unregistered) "@gmail.com" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_009 |  | Verify the email missing @ domain | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email (unregistered) "invalidemail.gmail.com" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_010 |  | Verify invalid email domain | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username email (unregistered) "invalidemaildomain@111.222.333" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_011 |  | Verify the invalid phone number with length more than 21 characters | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username phone number (unregistered) "978542215554454544589663" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_012 |  | Verify the invalid phone number contains string | 1. Go to site https://feature-qa-automation.customer-frontend.staging.aspireapp.com/sg/ 2. Enter Valid Username phone number (unregistered) "93789ghtrt" 3. Click "Next" button | Message should be shown: "Registered email or phone is invalid" | Error message |  | Medium | Erit Ha | 20/09/2021 | PASSED | Yes
| LOG_013 |  | Some other negative tests | [7 empty] | SKIP | No

## bug_Seller (hidden)
STT | Description bug | Platform | Type bug | Status | Fixed by | Reporter
1 | Order complete page (account: user3@yopmail.com/123456) - Show all info at Contact name is show wrong | Android, CA #330 | Minor | Fixed | N.Anh | Hằng
2 | Mua thành công product vs shipping fee 18k Sau đó mua product deal thì nó vẫn lưu lại 18k trong khi API show 0d | Android, CA #336 | Major | Fixed | N.Anh
3 | Mobile + web login chung 1 account Không refresh shopping cart page khi user mua hàng trên mobile | Web CA | Major | Fixed | Đại
4 | Product: Sản phẩm hết hàng mà check-out lại là: error.item.deleted | API CA | Major | Fixed | Huyền
5 | owner shop: Ko show error hủy hàng trong detail manage order and manage order của người bán hủy | WEB Staging |  | Fixed
6 | Mua hàng lần đầu bằng ATM ko dc | IOS staging 80 |  | Fixed
7 | API - ko mua hàng ATM thành công (cancel ngay OTP) mà vẫn show trên shop + buyer | API staging |  | Fixed
8 | E-voucher vào detail ko show 1 list danh sách mã code (0945) | iOS staging 83 |  | Fixed
9 | Sprint 31
10 | Có 1sp còn lại - Click add to cart button 2 lần --> Show "something went wrong. Please try again" 409 | API CA 31 |  | Fixed | Huyền | Hằng
11 | Edit product --> Show add to cart button và buy now là sai | Web CA31 |  | Fixed |  | Hằng
12 | - Add 2 loại variations (ví dụ màu xám và xanh) - Click chọn màu xám và add to cart - Click chọn màu xanh và click add to cart --> Show "something went wrong. Please try again" 409 | API CA 31 |  | Fixed | Huyền | Hằng
13 | - Go go shop profile (owner shop) - Click any product to go to detail have variation - Refresh page --> show 500 error | Web CA31 |  | Fixed | A Lợi | Hằng
14 | Android, iOS remove product của shopping cart --> Go back shopping cart vẫn show sản phẩm | API CA31 | Improve | Fixed | Huyền | Hằng
15 | Order history ko nên show tracking code = null | Android CA31 |  | Fixed | Phương | Hằng
16 | Nên show variation tại history order | Android CA31 |  | Fixed | Phương | Hằng
17 | Web: Go to home page (does not login) - Click tạo kênh bán hàng - Login account đã có shop (shopproduct@yopmail.com/123456) ---> Actual: show popup đăng kí và web đơ | Web 9-4 | Critical |  | Đại | Hằng
18 | Sp có nhiều variations. Thêm vài variation vào cart. Thay đổi quatity của 1 variation trong cart. => Variation cuối cùng trong cart cũng bị thay đổi theo. | Android CA31 |  | Fixed | N.Anh | Bảo
19 | Add nhiều variation của 1 sp vào cart. CHeck out cart Confirm page/Order complete page ko show đủ variation | Android CA31 |  | Fixed | N.Anh | Bảo
17 | Hết session sản phẩm còn số lượng thì vẫn cho đi tiếp Hiện tại khi confirm sẽ bị lỗi "something went wrong" | API CA 31 |  |  | Huyền | Bảo
18 | Xóa 1 variation (hoặc edit quantity), orderService chua syn dc | API CA 31 |  |  | Huyền | Bảo
20 | Xóa 1 item trong shopping cart --> API return về trễ..ko update đúng | API CA31 |  | Fixed | Huyền | Hằng
21 | - Voucher dien tu (co 3 cai), 1 shop (có 1 product), 1 shop có 2 product - Tại 1 shop có 2 product, input ghi chú thì nhảy lên nhảy xuống | iOS CA 398 | Minor | Skip | Hưng | Hằng
22 | Buy online => Back lại ở screen nhập số thẻ => Chọn COD => Shipping fee cộng thêm | API |  |  | Huyền | Bảo
23 | Đổi tên tại check out --> đến màn hình confirm tên ko dc đổi | PROD web |  | Fixed | Đại | Hằng
Sprint 32
24 | Owner shop không được quyền edit product deal ngoại trừ editor - Phải show hết hạn, hết hàng trên detail | COM web |  | Fixed | A Lợi | Hằng
25 | admin editor vào edit product deal --> save thì ra trang 404 | COM web |  | Fixed | A Lợi | Hằng
26 | API -> variation 1 có 5 cái --> Mà mua 10 cái vẫn được --> nên check số lượng còn lại | API COM |  | Fixed | Huyền | Hằng
27 | Điều kiện: variation 1 hết hàng - User click variation 1 --> thì nên show hết hàng | COM web |  | Fixed | A Lợi | Hằng
28 | docker-compose Giữa giỏ hàng và detail page do not match | API COM |  | Fixed | Đại | Hằng
29 | UI shopping cart bị bể với title name quá dài | WEB CA |  | Fixed | Đại | Hằng
30 | variation chua max lenght 20 ki tu | WEB CA |  | Fixed | A Lợi | Hằng
31 | cases normal và business khác discount shipping fee Câu hỏi (sẽ ưu tiên show thằng nào? giảm phí ntn?) --> A Cuong Đang giải quyết |  |  | Skip
32 | Không trừ shipping fee (lúc thanh toán) cho product ko co variation | API CA |  | Fixed | Huyền | Hằng
33 | product remain 3cai - user mua 3cai, xong van mua duoc nua | API CA | Critical | Fixed | Huyền | Hằng
34 | Android ko logout duoc | Android |  | Fixed | N.Anh
35 | DEAL --> tai man hinh delivery-info --> tru shipping fee ok đến màn hình mua thành công COD lại cộng shipping fee | API CA | Critical | Fixed | Huyền | Hằng
36 | Ko nhan dc SMS khi mua deal online |  |  |  | N.Anh | Bảo
37 | Email ko show item khi mua deal online |  |  |  | N.Anh | Bảo
38 | Search product, click on product => Crash App | Android CA 371 |  | Fixed | N.Anh | Bảo
39 | Back from delivery page về check out then Click back (browser) from shopping cart ko ra đc home page. |  |  |  |  | Bảo
Sprint 33
40 | Should check valid modelid (if any) when user check out | API CA |  | Fixed |  | Hằng
41 | /orderservices2/api/bc-orders/confirm-online/${bcId_1}/finish --> API trên sẽ được chặn khi mua bằng COD | API CA |  |  |  | Hằng
42 | https://mediastep.atlassian.net/browse/BC-3458 |  |  | Fixed |  | Hằng
43 | Luôn show hết hàng khi số lượng deal/product không đủ | Web staging |  | Fixed |  | Hằng
44 | Shipping free đang sai trên GHTK với price > 3M (insurance) | API staging |  | Fixed |  | Hằng
45 | Address tại confirmation show ko full nếu địa chỉ quá dài | IOS Staging |  | Fixed |  | Hằng
46 | Voucher giấy mua ATM lại thành voucher điện tử https://mediastep.atlassian.net/browse/BC-3460 | API staging |  | Fixed |  | Hằng
47 | Chỉ chặn COD > 10M cho group theo Deal hoặc shop | IOS Staging |  | Fixed |  | Hằng
48 | Mua e-voucher bằng COD --> Nhận hàng..trả tiền ko show status chưa dùng hoặc dùng rồi | IOS Staging |  | Fixed |  | Hằng
49 | Shipping plan show sai khi user edit thông tin tại confirm page Chuyển từ ATM -> COD | Android staging |  | Fixed |  | Hằng
50 | Shipping plan show sai khi user edit thông tin tại confirm page Chuyển từ COD -> ATM | IOS Staging |  | Fixed |  | Hằng
51 | Seller app
52 | Login 1 account chưa có shop trước đó --> Should be logged out when user press back and confirm Logout | Android, iOS dev |  | Fixed | N.Anh | Hằng
53 | Login shop account --> Data ko load --> Pull refresh mới load data lên | Android | Minor | Fixed | N.Anh | Hằng
54 | Không show Free icon trên mỗi item | Android |  | Fixed | N.Anh | Hằng
55 | Update shop profile chưa đúng - Link page ko show - Địa chỉ cửa hàng ko show - Quận huyện show mã code - Cùng địa chỉ lấy hàng thì collect thông tin địa chỉ lấy hàng lại | Android |  | Fixed | Phương | Hằng
56 | Tại shop profile --> camera icon tại avarta và banner nên có shadow | Android | Improve | Fixed | Phương | Hằng
57 | About us --> thiếu địa chỉ shop Tên thành phố nên là in-country | Android |  | Fixed | Phương | Hằng
58 | Create new account: Nên check error khi user tạo shop với email đã tồn tại | Android | Major | Fixed | N.Anh | Hằng
59 | Create new account: không tạo account mới được | Android | Critical | Fixed | N.Anh | Hằng
60 | Login account shop via FB --> App is crash | Android | Critical | Fixed | N.Anh | Hằng
61 | Login via FB --> Không show change password tại side menu | Android |  | Fixed | Phương | Hằng
62 | Xài tiếng việt --> nhưng upload cover và avarta thành công lại show english | Android |  | Fixed | N.Anh | Hằng
63 | - Crash edit profile | Android |  | Fixed | Phương | Bảo
64 | - Can't logout after post a product. | Android |  | Fixed | N.Anh | Bảo
65 | - Bottom bar miss after post a product. | Android |  | Fixed | N.Anh | Bảo
66 | Sidemenu: Click avarta hoặc tên shop --> Không nên đưa user đến trang edit thông tin user | Android |  | Fixed | N.Anh | Hằng
67 | Change password on another device A, => pop up log out show on device B but keep showing after log in again. | Android |  | Fixed | N.Anh | Bảo
68 | Edit profile: Thêm mô tả => Save lại thì mất cái địa chỉ shop ở "About us" | Android |  | Fixed | Phương | Bảo
69 | About-us: nên show full ten6 tỉnh và tên thành phố (hiện tại chỉ show 5 tp chính) | Android |  | Fixed | Phương | Hằng
70 | Edit shop profile: Nếu thay đổi thông tin địa chỉ và danh mục --> Show popup cảnh báo giống trên web | Android |  | Fixed | Phương | Hằng
71 | Tạo account => Tạo page xong vào edit profile thì thông tin địa chỉ shop bị mất. | Android |  | Fixed | Phương | Bảo
72 | Create new page: Default shop address should be shown user location | Android | Improve | Fixed | N.Anh | Bảo
73 | Remove API redundance -> Bên tab bên cạnh :D | Android API |  | Fixed | N.Anh | Hằng
74 | [Deal/Product detail] Click pending/rejected product deal ko thấy đc content, show a empty screen |  |  | Fixed | N.Anh | Bảo
75 | Đặt tên shop dài xíu thì line thứ 2 bị che không đọc đc |  |  | Fixed | N.Anh | Bảo
76 | [edit shop profile] Thêm mô tả nên cho viết xuống hàng. |  |  | Fixed | Phương | Bảo
77 | [User app] all deal ordered are disappeared | Android CA User | Critical | Fixed | Phương | Hằng
78 | [Management] Nên show số lượng trên từng filter như (All, To be confirm, Waiting for pickup...) | Android CA |  | Fixed | Phương | Hằng
79 | [Management] Number tại filter đang show không đúng | Android CA |  | Fixed | Phương | Hằng
80 | [Add info bank] Nên được scroll down/up khi keyboard show | Android CA |  | Fixed | N.Anh | Hằng
81 | [Add info bank] Thêm tài khoản ngân hàng chưa work | Android CA |  | Fixed | N.Anh | Hằng
82 | Translate ''FOR SELLER" to Vietnamese "KÊNH BÁN HÀNG" at login page | Android CA |  | Fixed | N.Anh | Bảo
83 | [Create page] "Thêm địa chỉ mới" chỉ khi nào user tick chọn thì mới mở ra, default thì ẩn các field điền địa chỉ mới đi. | Android CA |  | Fixed | Phương | Bảo
84 | [Thông tin ngân hàng] Câu đúng: "Beecow sẽ chuyển tiền tới bạn qua tài khoản ngân hàng này" | Android CA |  | Fixed | N.Anh | Bảo
85 | [Seller App][order detail] Click "Chat" button => Can't create chat room | Android CA |  | In-progress | N.Anh | Bảo
86 | [Seller App][Order detail] [Cancel status] Câu đúng: Đơn hàng hủy do người bán. Nếu đã thanh toán trực tuyến, Beecow sẽ chuyển tiền lại trong vòng 2-5 ngày làm việc. | Android CA |  | Fixed | Phương | Bảo
87 | [Seller App] Đơn hàng (pay = ATM) hủy bởi shop ko thấy nằm trong mục "Đã hủy" | Android CA |  | Fixed | Phương | Bảo
88 | Filter order status phải pull to refresh mới update content. Should auto update when filter | Android CA |  | Fixed | Phương | Bảo
89 | [Seller app] Confirm order => ko input đc ghi chú | Android CA |  | Fixed | Phương | Bảo
90 | [Waiting for pickup] Câu đúng: "Đơn hàng vận chuyển bởi [đơn vị vận chuyển]. Đang chờ nhà vận chuyển lấy hàng. " | Android CA |  | Fixed | Phương | Bảo
91 | [Shop profile] & [edit shop profile] Nếu English: Show city name is out-country Nếu Vietname: Show city name is in-country | Android CA |  | Fixed | N.Anh | Hằng
92 | [Pop up Confirm order] Những đơn hàng có trước khi seller change address thì lúc confirm vẫn show địa chỉ pickup cũ Địa chỉ mới chỉ affect cho đơn hàng mới thôi. | Android CA | Major | Fixed | Phương | Bảo
93 | Filter order: Status đã hủy phải bao gồm tất cả các order bị hủy (buyer/seller hủy, buyer/seller từ chối giao nhận, hệ thống hủy) |  |  | Fixed | Phương | Bảo
94 | [Edit shopprofile] Edit thêm mô tả..khi xuống dòng là nó ẩn mất header cũng như footer :D | Android CA |  | Fixed | N.Anh | Hằng
95 | [Edit shopprofile] Khi change categories hoặc địa chỉ lấy hàng --> Lưu show popup warning --> Khi user click đã hiểu thì nên auto lưu (không nên để user phải click nút lưu 1 lần nữa) | Android CA |  | Fixed | Phương | Hằng
96 | [Edit shopprofile] tại mục thêm mô tả..nên có thêm icon edit --> để user biết là có thể edit được :D | Android CA | Improve | Skip | Phương | Hằng
97 | "Có x kiện hàng trong đơn hàng" => Kiện hàng sửa thành "món" cho hợp lý nhé (web/ios show là món) |  |  | Fixed | Phương | Bảo
98 | https://mediastep.atlassian.net/browse/BC-3725 [Mobile] [Seller app] As seller role, Should be shown [General info] and [Pickup address] at about us tab of shop profile | Android CA |  | Fixed | N.Anh | Hằng
99 | [Post product] Categories ko update khi user update categories tại shop profile | Android CA |  | Fixed | N.Anh | Hằng
100 | Tại shop profile --> location và url shop ko show |  |  | Fixed | Hưng | Hằng
101 | Change Vietnamese language --> shop, reviews, about us... chưa change |  |  | Fixed | Hưng | Hằng
102 | Nên show "edit your page" thay vì show "create a page" |  |  | Fixed | Hưng | Hằng
103 | Edit profile --> Click save (chức năng này chưa work) |  |  | Fixed | Hưng | Hằng
104 | About us --> tại address ko show district khi edit shop profile |  |  | Fixed | Hưng | Hằng
105 | Side menu --> bị lệch rating trên iPHone 6plus |  |  | Fixed | Hưng | Hằng
106 | xài tiếng việt --> logout show english |  |  | Fixed | Hưng | Hằng
107 | Upload product: Show popup đã tạo page mới thành công khi click upload product lần đầu |  |  | Fixed | Hưng | Hằng
108 | Upload product: bị trắng màn hình khi upload product thành công |  |  | Fixed | Hưng | Hằng
109 | - Remove referral field when edit page. |  |  | Fixed | Hưng | Bảo
110 | - Remove button Save & policy statement |  |  | Fixed | Hưng | Bảo
111 | - Remove deal category when edit shop profile |  |  | Fixed | Hưng | Bảo
112 | - Shop address is clean if same as pickup address |  |  | Fixed | Hưng | Bảo
113 | - Create account => Create page => Swipe screen right => Log out. |  |  | Fixed | Hưng | Bảo
114 | - Them 1 variation screen auto scroll up |  |  | Fixed | Hưng | Bảo
115 | Home: Product deal không có show edit icon |  |  | Fixed | Hưng | Hằng
116 | Home: Product deal hết hạn hay hết hàng đều phải show hết |  |  | Fixed | Hưng | Hằng
117 | Side menu: không show cửa hàng uy tín cho những shop được verified |  |  | Fixed | Hưng | Hằng
118 | About us missing description about shop. |  |  | Fixed | Hưng | Bảo
119 | Edit profile missing "About us" section (để cho seller viết giới thiệu về shop của họ) |  |  | Fixed | Hưng | Bảo
120 | Side menu: Click side menu --> thông tin shop bị flicker |  |  | Fixed | Hưng | Hằng
121 | Edit shop profile: Nếu thay đổi thông tin địa chỉ và danh mục --> Show popup cảnh báo giống trên web |  |  | Fixed | Hưng | Hằng
122 | About-us: nên show full tên tỉnh và tên thành phố (hiện tại chỉ show 5 tp chính) |  |  | Fixed | Hưng | Hằng
123 | Tab Thông tin ngân hàng ko show đúng info, (ko biết làm chưa :D) |  |  | Skip | Hưng | Bảo
124 | Should not auto scroll up when switch betteen "About us, Review..." |  |  | Skip | Hưng | Bảo
125 | Remove API redundance -> bên tab bên cạnh :D |  |  | Fixed | Hưng | Hằng
126 | Remove edit button on product deal (pending/rejected) |  |  | Fixed | Hưng | Bảo
127 | [Product detail] Click pending/rejected product deal ko thấy đc content, show a empty screen |  |  | Fixed | Hưng | Bảo
128 | [Management] Nên show số lượng trên từng filter như (All, To be confirm, Waiting for pickup...) | iOS CA |  | Fixed | Hưng | Hằng
129 | [Management] Nếu mua = COD (mà bị hủy) --> Thì show là Cancelled | iOS CA |  | Fixed | Hưng | Hằng
130 | [Management] filter bị mất highlight khi user click sidemenu or notify or vào detail | iOS CA |  |  | Hưng | Hằng
131 | [Add info bank] số cmnd là optional | iOS CA |  |  | Hưng | Hằng
132 | [Shop profile] Filter (chờ duyệt, đã đăng, từ chối) không highlight khi được chọn - Click filter --> Show dropdown list thì nên show gray color below dropdown list | iOS CA |  |  | Hưng | Hằng
133 | [Shop profile] [Filter] Click filter nó show dropdown list, Click filter again/outside of filter section --> nên đóng filter | iOS CA |  |  | Hưng | Hằng
134 | [Order pay = COD] buyer/seller cancel (từ chối nhận hàng/shop ko giao hàng) order đó thì status ko phải là "Hoàn tiền". Đã hủy mới đúng | IOS CA |  |  | Hưng | Bảo
135 | [Edit shop profile] Chỉ show warning popup khi edit categories và thông tin địa chỉ shop | iOS CA |  |  | Hưng | Hằng
136 | Sắp xếp lại thứ tự status trong mục filter: All => To be confirm => Waiting for pickup => Shipping => Shipped => Canceled => Refund |  |  |  | Hưng | Bảo
137 | https://mediastep.atlassian.net/browse/BC-3725 [Mobile] [Seller app] As seller role, Should be shown [General info] and [Pickup address] at about us tab of shop profile | iOS CA |  |  | Hưng | Hằng
138 | Webhook GHTK call status 7 - Ko lay dc hang => API tra ve "error.order.deliveryOrder.status.nextValueNotAllowed" Should be return "Success" and update order => CANCELED - Seller reject | Web API |  | Fixed | Huyền | Bảo
139 | Deal COD: Shipping --> Shipped error 500 | Web API |  | Fixed | Đại | Hằng
140 | Filter product status (public/pending/rejected) pending & rejected ko update number trong list dropdown (logout/login lại mới affect) |  |  |  | Hưng | Bảo
141 | Lúc switch qua lại các tab "Cửa hàng" or "Thông tin ngân hàng" thì title của tab cần show đủ |  |  |  | Hưng | Bảo
142 | Lỗi 400 khi cancel đơn hàng | Web CA, COM
143 | https://mediastep.atlassian.net/browse/BC-3786 | API CA
Note on E101: Y: Task này chưa cần sửa. nên[Skip] nhé. Để thống nhất design, tập trung cái quan trọng hơn.

## Bug_userBeecow (hidden)
STT | Description bug | Platform | Type bug | Status | Fixed by | Reporter
Sprint 34
1 | [Ordered history DEAL] Giao hàng thành công --> Text show thiếu tên nhà vận chuyển | IOS CA |  | Fixed | Hưng | Hằng
2 | [Ordered history Deal] [Order history PRODUCT] Thiếu filter Đợi lấy hàng | IOS CA |  | Fixed | Hưng | Hằng
3 | [Ordered history DEAL] tab filter giao hàng thành công --> show "something went wrong" | IOS CA | Critical | Fixed | Hưng | Hằng
4 | [Order detail - Shipping] Bỏ câu "Waiting for Delivery Service picking up package" |  |  | Fixed | Hưng | Bảo
5 | [Order history] Sometimes, app is crashed - Go to product ordered history --> filter giao hàng thành công - Go to deal ordered history --> App is crash | iOS CA |  | Fixed | Hưng | Hằng
6 | [Order history PROD] Order (waiting for pickup) ko thấy hiện Mã Vận đơn | IOS CA |  | Fixed | Hưng | Bảo
7 | [Delivery info Screen] app is crashed khi user input ghi chú | IOS CA | Critical | Fixed | Hưng | Hằng
8 | [Order history ] Thêm status Waiting for pickup |  |  | Fixed | Hưng | Bảo
9 | Order history - Filter deal shiped bị lỗi "Something went wrong" |  |  | Fixed | Hưng | Bảo
10 | [Deal history] Deal type voucher of merchant -> Go to detail (does not show voucher_code + lack status) | IOS CA |  | Fixed | Hưng | Hằng
11 | [Order success] [Voucher of merchant] 1. Does not show voucher_code when user order DEAL type voucher of merchant 2. Voucher_code show the same https://mediastep.atlassian.net/browse/BC-3650 | IOS CA | Critical | Fixed | Hưng | Hằng
12 | https://mediastep.atlassian.net/browse/BC-3667 | IOS CA |  | Fixed | Hưng | Hằng
13 | https://mediastep.atlassian.net/browse/BC-3677 | IOS Staging |  | Fixed | Hưng | Hằng
14 | https://mediastep.atlassian.net/browse/BC-3549 --> ticket này work chưa đúng | iOS CA |  | Fixed | Long | Hằng
15 | https://mediastep.atlassian.net/browse/BC-3792 |  |  | Fixed | Lanh | Bảo
16 | https://mediastep.atlassian.net/browse/BC-3801 |  |  | Fixed | Lanh | Hằng
17 | https://mediastep.atlassian.net/browse/BC-3797 | iOS CA |  | Fixed | Lanh | Bảo
18 | https://mediastep.atlassian.net/browse/BC-3802 |  |  | Fixed | Lanh | Hằng
18 | [Order history DEAL] Filter all are empty | Android CA | Critical | Fixed | Phương | Hằng
19 | [Order history PROD/DEAL] item waiting for pickup --> ko show status "Waiting for Delivery Service picking up package" | Android CA |  | Fixed | Phương | Hằng
20 | [Delivery Method screen] Ko đc redirect user sang item detail screen khi họ touch vào item image. | Android CA |  | Fixed | N.Anh | Bảo
21 | https://mediastep.atlassian.net/browse/BC-3648 [Deal history] voucher_code does not show for voucher of merchant (seller input code manual) | Android CA | Critical | Fixed | Phương | Hằng
22 | [Order success] The voucher_code does not show when user order DEAL type voucher of merchant successfully | Android CA |  | Fixed | Phương | Hằng
23 | Mua DEAL = ATM --> Show 500 error | Web | Critical | Fixed | Huyền | Hằng
24 | Webhook: shipping -> shipped --> response 500 error | API | Critical | Fixed | Huyền | Hằng
25 | [Confirm screen] Shipping to Kim Động district, Hưng yên --> Response 500 https://mediastep.atlassian.net/browse/BC-3636 | API |  |  | Huyền | Hằng
26 | [Web] [Shipping plan] Giaohangnhanh "1 hôm nay" text should be changed to "1 ngày" text https://mediastep.atlassian.net/browse/BC-3637 | Web CA |  |  | Đại | Hằng
27 | [Deal] Mua voucher of merchant COD/ATM --> response 500 | API |  |  | Huyền | Hằng
28 | https://mediastep.atlassian.net/browse/BC-3681 | Web staging |  |  | Đại | Hằng
29 | https://mediastep.atlassian.net/browse/BC-3680 | Web staging |  |  | Đại | Hằng
30 | Filter Chờ xác nhận lại Show status đang giao hàng | API Staging |  |  | Huyền | Hằng
31 | Filter order status phải pull to refresh mới update content. Should auto update when filter | Android CA |  | Fixed | Phương | Bảo
32 | Lỗi 400 khi cancel đơn hàng | Web CA, COM |  |  |  | Hằng
33 | https://mediastep.atlassian.net/browse/BC-3786 | API CA |  |  |  | Hằng
34 | https://mediastep.atlassian.net/browse/BC-3791 | API CA |  |  |  | Bảo
35 | https://mediastep.atlassian.net/browse/BC-3793 | Web CA, COM |  |  |  | Hằng
36 | https://mediastep.atlassian.net/browse/BC-3795 | API CA |  |  |  | Bảo
37 | https://mediastep.atlassian.net/browse/BC-3796 | API CA |  |  |  | Bảo
38 | https://mediastep.atlassian.net/browse/BC-3798 | API CA |  |  |  | Bảo
39 | https://mediastep.atlassian.net/browse/BC-3805 | API CA |  |  |  | Hằng
40 | https://mediastep.atlassian.net/browse/BC-3809 | API CA |  |  |  | Hằng
41 | https://mediastep.atlassian.net/browse/BC-3810 | API CA |  |  |  | Hằng

## Remove API redundance (hidden)
Android | Note | IOS
For seller Screen (màn hình giao diện login cho người bán)
https://api.mediastep.ca/orderservices2/api/my/bc-orders/products?status=all&page=0&size=20
https://api.mediastep.ca/notifyservices/api/user/notifications
Login seller success (Home page)
https://api.mediastep.ca/orderservices2/api/shop-carts/my-shop-cart-info | Đã remove tính năng Shopping cart
https://api.mediastep.ca/orderservices2/api/my/bc-orders/products?status=all&page=0&size=20
Tại Home page thì ko nên load những API này
https://api.mediastep.ca/reviewservices/api/store-review/get-overview-by-store-id?storeId=3145 | Mở app ko nên gọi API này trước: Gọi vì muốn Shop profile mở tab review UI ko bị nháy chớp dựt
https://api.mediastep.ca/reviewservices/api/store-review/get-by-store-id?size=20&page=0&storeId=3145 | Mở app ko nên gọi API này trước: Gọi vì muốn Shop profile mở tab review UI ko bị nháy chớp dựt
https://api.mediastep.ca/reviewservices/api/store-review/get-by-store-id?size=20&page=1&storeId=3145 | Mở app ko nên gọi API này trước: Gọi vì muốn Shop profile mở tab review UI ko bị nháy chớp dựt
https://api.mediastep.ca/api/authenticate/switch-profile | Chỉ mỗi app seller ko cần API switch user -> shop : Cần gọi để có Shop Token
https://api.mediastep.ca/storeservice/api/store/about/3145 | Mở app ko nên gọi API này trước: Gọi vì muốn Shop profile mở tab about UI ko bị nháy chớp dựt
https://api.mediastep.ca/catalogservices/api/terms?taxonomy=product-catalog&level=0&metadata=productCatalogType:PRODUCT | Cần gọi để lấy đc danh sách category cho Post product
https://api.mediastep.ca/itemservice/api/store/get-item-of-my-store?size=20&page=0&reviewStatus=APPROVED | API này gọi 4 lần
https://api.mediastep.ca/catalogservices/api/terms/1001/tree | Gọi double khi click vào detail page
https://api.mediastep.ca/orderservices2/api/shop-carts/my-shop-cart-info | Close detail page lại gọi API này --> nên remove luôn mọi nơi